## Project Plan

Purpose of the Summit: Implement first major public engagement event; provide linkages to professional development; assess states’ needs in policy and economic areas with regard to International Ed

| Day of Summit – September 18 BEFORE | Who | Time |
| --- | --- | --- |
| Bring all supplies to HUB - packets (Grace) - nametags (Grace) - on-site registration forms (Grace) - signs (Michele) - boxes for forms (Michele) - registration contact forms (Michele) - food for Resource Fair (Michele) | Michele, Grace | 8:00 am at Loading Dock |
| Post signs in HUB and breakout rooms | volunteer | 8:15 am |
| Set up VCR for video | Michael | 8:15 am |
| Check sound equipment - mikes in ballroom - sound system - other? (other rooms?) | Michael | 8:15 am |
| Check ballroom setup - main table (# of chairs) - round tables: maps, candy, Where do we go from here? forms | Michele volunteer | 8:15 am |
| Check volunteer assignments | Grace, Michele | 8:30 am |
| Set up Refreshment tables - coffee, tea | Starbucks | 8:35 am |
| Set up Registration table | Grace | 8:35 am |
| Check Resource table area - help early groups set up | Nancy | 8:35 am |
| Start Global Sound CD (plus live music for Registration?) | Global Sound CD | 8:45 am |
| Registration opens - with helpers | Grace | 8:45 am |
| UBS sets up table with books for sale | UBS | 8:45 am |
| Sound checks with mikes | Michael Grace, Natalya | 9:05 am |

| Day of Summit – September 18 DURING | Who/Where | Time |
| --- | --- | --- |
| Start video | Michael | 9:17 am |
| Student Opening | Grace Wang, Students from OneWorld Now! | 9:30 am |
| Lunch delivery | Loading Dock (Uwajimaya) | 11:30 am |
| Announce lunch | Michele | 12:00 pm |
| Transition to Session #2 | Michele | 1:15 pm |
| Summit closes - remind about “Where do we go” piece - update Contact sheet and decide about involvement - exit Ballroom quickly (or move to north-end) | Dave HUB Ballroom | 2:45 pm |
| Set up Refreshments - leftover Starbucks? - Food from Costco | HUB Ballroom | 3:00 pm |
| Set up Resource Fair - set up tables and displays | WAC in HUB Ballroom | 3:00 pm |
| Resource Fair opens | WAC in HUB Ballroom | 3:30 pm |

COMPLETE

| Task | Resources | Est. Date | Actual Date |
| --- | --- | --- | --- |
| Week of September 8 |  |  |  |
| Send draft of policy piece to Nancy WAC for review | Nancy, Michele, Kristin | Sep 8 | Sep 8 |
| Arrange for assembling packets | Hamilton? (Sue) | Sep 8 | Sep 11 |
| Confirm bentos with Uwajimaya - make-up of bentos - veggie bentos (30%) - final cost per - confirm date for final count | Toshi | Sep 8 | Sep 9 |
| Confirm schedule with all presenters and technology needs (by email) | Michele | Sep 8 | Sep 9 |
| Identify Tech Crew (sound person) | Michael North | Sep 8 | Sep 9 |
| Confirm Starbucks for coffee, tea - 8:45 am - 3:00 pm | Starbucks | Sep 9 | Sep 11 |
| Check on Global Sound CD | Global Sound contact | Sep 9 | Sep 9 |
| Arrange for other food - water (Toshi for lunch) - pick up snacks from Costco | Michele _________ | Sep 9 | Sep 9 |
| Get final version of Where do we go from here? | David W | Sep 10 | Sep 10 |
| Revise policy piece and submit for graphic design | Michele, Richard Thornton | Sep 13 | Sep 12 |
| Get final arrangements at HUB | HUB Res | Sep 12 | Sep 12 |

| Week of September 8 |  |  |  |
| --- | --- | --- | --- |
| Draft evaluation, contact form using mail merge, on-site registration | Michele | Sep 13 | Sept 13 |
| Organize volunteers for Summit - Registration - Handing out packets - Room monitors - Food - Coalition table - Collect Summit forms) | Michele | Sep 13 | Sept 14 |
| Review Summit opening with students | Michele, Kristin, Grace Wang, OneWorld student | Sep 13 | Sept 14 |
| Get food at Costco? - candy for breakout sessions? - napkins? - little bowls? - table cloths? | Michele, Costco | Sep 13 | Sept 17 |
| Draft signs for Summit - for breakout rooms - for input? - Summit HUB Ballroom signs to post | Michele | Sep 14 | Sept 17 |
| Design opening session to make it interactive. Decide on props. | Michele | Sep 14 | Sept 15 |
| Get supplies at Office Depot - pens for tables? | Michele, Office Depot | Sep 14 | -- |

| Task | Resources | Est. Date | Actual Date |
| --- | --- | --- | --- |
| Week of September 15 |  |  |  |
| Get policy piece to World Affairs Council for printing | WAC, Nancy Michele | Sep 15 | Sept 16 |
| Print for packet: - Where Do We Go From Here - MLA language piece (at LLC?) - web home page with Coalition mission? | Ram printing Michele | Sep 15 | Sept 15 |
| Confirm final arrangements with HUB | Nancy, Mary, Michele, LLC, HUB | Sep 16 | Sept 15 |
| Print final Summit Schedule | Ram printing Michele | Sep 16 | Sept 16 |
| Get packet materials gathered from Asia Society | Grace | Sep 16 | Sept 16 |
| Get packet materials from iEarn | Kristi | Sep 16 | Sept 16 |
| Get photocopies of James Banks article from Hamilton | Sue R | Sep 16 | Sept 16 |
| Pick up Peechees from UBS | UBS Michele | Sep 16 | Sept 16 |
| Update registration DB and print out name tags | Michele, Grace | Sep 16 | Sept 17 |
| Assemble packets at LLC | LLC | Sep 16 7 pm | Sept 16 |
| Give Uwajimaya final count for bentos | Uwajimaya | Sep 17 am | Sept 17 |
| Pick up final food from Costco | Michele? | Sep 17 | Sept 17 |
| Final update of registration DB and print out any additional name tags | Michele, Grace | Sep 17 | Sept 17 |